## 18_07_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [23 empty] | Report Date: 18 Jully, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [22 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 04-03-2020 | 04-10-2020 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020 | 23-05-2020 | 30-05-2020 | 06-06-2020 | 13-06-2020 | 20-06-2020 | 27-06-2020 | 04-07-2020 | 11-07-2020 | 18-07-2020 | 25-07-2020 | 01-08-2020 | 08-08-2020 | 15-08-2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | n | n | n | n | n | n | n |  |  |  | q | q | q | q | A
| l |  |  |  |  | 1.2 | Making the project responsive | [15 empty] | m | l
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | n | n | n | n | n | n | n | n | n | n | q | q | q | q | A
| l |  |  |  |  | 3 | Build handover session from Dev team to QA team | [5 empty] | l | [6 empty] | n | n | n | n | n | n | n | n | q | q | q | q | A
|  | l |  |  |  | 4 | Test Case Execution | [25 empty] | A | bar: n to l q
|  | l |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances |  |  |  | n: n; n: n; n: n; m n: n; l n: q; l n: q; l n: q; l n: n; l q: q; l q: q; l q: q; l q: q; l A: A
|  | l |  |  |  | 6 | QA team certifies for internal release of the build |  |  |  | l n: l; l n: l; l n: l; l n: n; l q: q; l q: q; l q: q; l q: q | A
|  |  | l |  |  | 7 | Internal / External Demo - at the end of Sprint Release | [16 empty] | l | l | l | n | q | q | q | q | A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | q | q | q | q | q | q | bar: l to A
[5 empty] | m | 9 | Product Delivery | bar: q to A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | Delivery of the product can be delayed only if structure of the project is changed or new Business logic is applied. | bar: n; A
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 | 16 May'2020 | 23 May'2020 | 30 May'2020 | 06 June'2020 | 13 June'2020 | 20 June'2020 | l: 27 June'2020; l: 07 Jully'2020; l: 11 Jully'2020; n: 18 Jully'2020; A: Vivek | Milan
The project started on 9th March 2020 and the estimated completion date is 29th May 2020, we expect to increase this duration upto 15th August 2020
As per the demo with Kunal Singh Vaghela and Raj Baveja the deadline will be 15th August 2020 and project scope may increased.
[11 empty] | m | l | q
[10 empty] | Wingdings | m | l | q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 11_07_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [19 empty] | Report Date: 11 Jully, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [18 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 04-03-2020 | 04-10-2020 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020 | 23-05-2020 | 30-05-2020 | 06-06-2020 | 13-06-2020 | 20-06-2020 | 27-06-2020 | 04-07-2020 | 11-07-2020 | 18-07-2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | n | n | n | n | n | n | n |  |  |  | A
| l |  |  |  |  | 1.2 | Making the project responsive | [15 empty] | m | l
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | n | n | n | n | n | n | n | n | n | q | A
| l |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; n: n; n: n; n: n; m n: n; l n: n; l n: n; l n: n; l q: q; l A: A
|  | l |  |  |  | 4 | Test Case Execution | [21 empty] | A | bar: n to l q
|  | l |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances |  |  |  | n: n; n: n; n: n; m n: n; l n: q; l n: q; l n: q; l q: q; l A: A
|  | l |  |  |  | 6 | QA team certifies for internal release of the build | [21 empty] | A | bar: l n to l q
|  |  | l |  |  | 7 | Internal / External Demo - at the end of Sprint Release |  |  |  | l n: l; l n: l; l n: l; l q: q; l A: A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | q | q | q | q | q | q | q | q | q | q | A
[5 empty] | m | 9 | Product Delivery | bar: l q to l A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | Delivery of the product can be delayed due to delayed supply of SSL | bar: l n; l A
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 | 16 May'2020 | 23 May'2020 | 30 May'2020 | 06 June'2020 | 13 June'2020 | 20 June'2020 | 27 June'2020 | 07 Jully'2020 | 11 Jully'2020 | 18 Jully'2020 | Vivek | Milan
The project started on 9th March 2020 and the estimated completion date is 29th May 2020, we expect to increase this duration upto 18th Jully 2020
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 04_07_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [19 empty] | Report Date: 04 Jully, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [17 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 04-03-2020 | 04-10-2020 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020 | 23-05-2020 | 30-05-2020 | 06-06-2020 | 13-06-2020 | 20-06-2020 | 27-06-2020 | 04-07-2020 | 11-07-2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | n | n | n | n | n | n | n |  |  | A
| l |  |  |  |  | 1.2 | Making the project responsive | [15 empty] | m | l |  |  |  | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | n | n | n | n | n | n | n | n | q | A
| l |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; n: n; n: n; n: n; m n: n; l n: n; l n: n; l q: q; l A: A
|  | l |  |  |  | 4 | Test Case Execution | [21 empty] | A | bar: n to l q
|  | l |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances |  |  |  | n: n; n: n; n: n; m n: n; l n: q; l n: q; l q: q; l A: A
|  | l |  |  |  | 6 | QA team certifies for internal release of the build | [21 empty] | A | bar: l n to l q
|  |  | l |  |  | 7 | Internal / External Demo - at the end of Sprint Release |  |  |  | l n: l; l n: l; l q: q; l A: A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | q | q | q | q | q | q | q | q | q | A
[5 empty] | m | 9 | Product Delivery | bar: l q to l A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | Delivery of the product can be delayed by delayed supplied of SSL for www.globaltradesdata.com | bar: l n; l A
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 | 16 May'2020 | 23 May'2020 | 30 May'2020 | 06 June'2020 | 13 June'2020 | 20 June'2020 | 27 June'2020 | 07 Jully'2020 |  | Vivek | Jignesh | Milan
The project started on 9th March 2020 and the estimated completion date is 29th May 2020, we expect to increase this duration upto 11th Jully 2020
Project is delaying as SSL is not provided for the website. Note : Work for major task 6 and 7 is in progress so sub objective is displayed with filled circle. However major task in schedule is prolonged.
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 27_06_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [19 empty] | Report Date: 27 June, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [16 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 04-03-2020 | 04-10-2020 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020 | 23-05-2020 | 30-05-2020 | 06-06-2020 | 13-06-2020 | 20-06-2020 | 27-06-2020 | 04-07-2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | n | n | n | n | n | n | n |  | A | A
[6 empty] | 1.2 | Making the project responsive | [15 empty] | m | l | m |  |  | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | n | n | n | n | n | n | n | q | A | A
| l |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; n: n; n: n; n: n; m n: n; l n: n; m q: q; m A: A; m A: A
|  | l |  |  |  | 4 | Test Case Execution | [21 empty] | A | bar: n to m q
|  | l |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances |  |  |  | n: n; n: n; n: n; m n: n; l n: q; m q: q; m A: A; m A: A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [21 empty] | A | bar: l n to m q
|  |  | m |  |  | 7 | Internal / External Demo - at the end of Sprint Release |  |  |  | l n: l; m q: m; m A: A; m A: A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | q | q | q | q | q | q | q | q | A | A
[5 empty] | m | 9 | Product Delivery | bar: m q to m A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | Delivery of the product can be delayed by delayed supplied of SMTP Server and Stripe Live API Keys | bar: l to l n; m A
[6 empty] | 2 | Lack of resource in QA can affect the product delivery date | [20 empty] | A | bar: n to l n
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 | 16 May'2020 | 23 May'2020 | 30 May'2020 | 06 June'2020 | 13 June'2020 | 20 June'2020 | 27 June'2020 |  | Vivek | Hardik | Jignesh | Milan
The project started on 9th March 2020 and the estimated completion date is 29th May 2020, we expect to increase this duration upto 4th Jully 2020
Project will be complet on Monday (30th June 2020). However QA is aligned with other projects
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 20_06_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [19 empty] | Report Date: 20 June, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [16 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 04-03-2020 | 04-10-2020 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020 | 23-05-2020 | 30-05-2020 | 06-06-2020 | 13-06-2020 | 20-06-2020 | 27-06-2020 | 04-07-2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | n | n | n | n | n | n | q |  | A | A
[6 empty] | 1.2 | Making the project responsive | [15 empty] | m | m | m |  |  | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | n | n | n | n | n | n | q | q | A | A
| l |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; n: n; n: n; n: n; m n: n; m q: q; m q: q; m A: A; m A: A
|  | l |  |  |  | 4 | Test Case Execution | [21 empty] | A | bar: n to m q
|  | l |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances |  |  |  | n: n; n: n; n: n; m n: n; m q: m; m A: A; m A: A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [21 empty] | A | bar: m q to m q
|  |  | m |  |  | 7 | Internal / External Demo - at the end of Sprint Release | bar: m q to m A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | q | q | q | q | q | q | q | q | A | A
[5 empty] | m | 9 | Product Delivery | bar: m q to m A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | Delivery of the product can be delayed by delayed supplied of SMTP Server and Stripe Live API Keys | bar: l to m n; m A
[6 empty] | 2 | Delivery of the product can be delayed due to lack of resource in Development Department | [20 empty] | A | bar: n to m n
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 | 16 May'2020 | 23 May'2020 | 30 May'2020 | 06 June'2020 | 13 June'2020 | 20 June'2020 |  |  | Vivek | Hardik | Jignesh | Milan
The project started on 9th March 2020 and the estimated completion date is 29th May 2020, we expect to increase this duration upto 27th June 2020
Project development will be completed on 22nd June 2020, however making the project responsive will reamain as Jignesh (person who will do this task) is occupied with other project.
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 13_06_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [16 empty] | Report Date: 13 June, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [14 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 04-03-2020 | 04-10-2020 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020 | 23-05-2020 | 30-05-2020 | 06-06-2020 | 13-06-2020 | 20-06-2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | n | n | n | n | n | q | A | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | n | n | n | n | n | q | A | A
| l |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; n n: n; n n: n; n n: n; q q: q; A A: A; A A: A
|  | l |  |  |  | 4 | Test Case Execution | [18 empty] | A | bar: n n to q q
|  | l |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances |  |  |  | n n: n; n n: n; n n: n; q q: m; A A: A; A A: A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [18 empty] | A | bar: q q
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | bar: q q to A A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | q | q | q | q | q | q | A | A
[5 empty] | m | 9 | Product Delivery | bar: A A to A A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | Delivery of the product can be delayed by delayed supplied of SMTP Server and Stripe Live API Keys | bar: l to n n; A A
[6 empty] | 2 | Delivery of the product can be delayed due to lack of resource in QA Department | [18 empty] | A | bar: n n to n n
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 | 16 May'2020 | 23 May'2020 | 30 May'2020 | 06 June'2020 | 13 June'2020 |  | Vivek | Hardik | Milan
The project started on 9th March 2020 and the estimated completion date is 29th May 2020, we expect to increase this duration upto 20th June 2020
QA Team Tested Customer UI part, however Admin Panel is yet to be tested, in Code development micro level UI changes are started under the guidance of Pratik Jain.
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 06_06_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [15 empty] | Report Date: 06 June, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [13 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 04-03-2020 | 04-10-2020 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020 | 23-05-2020 | 30-05-2020 | 06-06-2020 | 13-06-2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | n | n | n | n |  | A | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | n | n | n | n | q | A | A
| l |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; n: n; n: n; q: q; A: A; A: A
|  | l |  |  |  | 4 | Test Case Execution | [17 empty] | A | bar: n to q
|  | l |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances |  |  |  | n: n; n: n; q: q; A: A; A: A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [17 empty] | A | bar: q
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | bar: q to A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | q | q | q | q | q | A | A
[5 empty] | m | 9 | Product Delivery | bar: q to A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | Delivery of the product can be delayed by delayed supplied of SMTP Server and Stripe Live API Keys | bar: l to n; A
[6 empty] | 2 | Delivery of the product can be delayed due to lack of resource in QA Department | [17 empty] | A | bar: n
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 | 16 May'2020 | 23 May'2020 | 30 May'2020 | 06 June'2020 |  | Vivek | Hardik | Milan
The project started on 9th March 2020 and the estimated completion date is 29th May 2020, we expect to increase this duration upto 13th June 2020
QA Team Tested Customer UI part, however Admin Panel is yet to be tested, Right now QA Teams are busy with VMI and WLS. They will test Admin Panel when they get time and permission of Luvdeep.
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 30_05_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [14 empty] | Report Date: 30 May, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [12 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 04-03-2020 | 04-10-2020 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020 | 23-05-2020 | 30-05-2020 | 06-06-2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | n | n | n |  | A | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | n | n | n | q | A | A
| l |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; n: n; q: q; A: A; A: A
|  | l |  |  |  | 4 | Test Case Execution | [16 empty] | A | bar: n to q
|  | l |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances |  |  |  | n: n; q: q; A: A; A: A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [16 empty] | A | bar: q
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | bar: q to A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | q | q | q | q | A | A
[5 empty] | m | 9 | Product Delivery | bar: q to A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | Delivery of the product can be delayed by delayed supplied of SMTP Server and Stripe Live API Keys | bar: l to n
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 | 16 May'2020 | 23 May'2020 | 30 May'2020 |  | Vivek | Hardik | Milan
Labels
The project started on 9th March 2020 and the estimated completion date is 29th May 2020, we expect to increase this duration upto 6th June 2020
Project demo to Kunalsingh Vaghela and Raj Baveja (OCR owner) on 25th May 2020 was successful.
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 23_05_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [14 empty] | Report Date: 23 May, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [12 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 04-03-2020 | 04-10-2020 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020 | 23-05-2020 | 30-05-2020 | 06-06-2020
[20 empty] | m | m
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | n | n | m | m | A | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | n | n | m | m | A | A
| m |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; m m m: m; m m m: m; m A A: A; m A A: A
|  | m |  |  |  | 4 | Test Case Execution | [16 empty] | A | bar: m m m to m m m
|  | m |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | bar: m m m to m A A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [16 empty] | A | bar: m m m to m m m
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | bar: m m m to m A A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | q | q | m | m | A | A
[5 empty] | m | 9 | Product Delivery | bar: m m m to m A A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | Constant changes in scope may affect the delivery, quality of the Product. | bar: l to n n
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 | 16 May'2020 | 23 May'2020 |  |  | Vivek | Hardik | Milan
Labels
The project started on 9th March 2020 and the estimated completion date is 29th May 2020, we expect to increase this duration upto 6th June 2020
Currently we are working as per the client requirement on day to day bases, code development and build process too are happening day to day basis.
Project demo to the client is scheduled on 25th May 2020.
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 16_05_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [13 empty] | Report Date: 16 May, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [11 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 04-03-2020 | 04-10-2020 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020 | 23-05-2020 | 29-05-2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | n | m | m | A | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | n | m | m | A | A
| m |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; m m: m; m m: m; A A: A; A A: A
|  | m |  |  |  | 4 | Test Case Execution | [15 empty] | A | bar: m m to m m
|  | m |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | bar: m m to A A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [15 empty] | A | bar: m m to m m
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | bar: m m to A A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | q | m | m | A | A
[5 empty] | m | 9 | Product Delivery | bar: m m to A A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | Any change in the scope will affect the project delivery schedule. | bar: l to n n
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 | 16 May'2020 |  |  | Vivek | Hardik | Milan
Labels
The project started on 9th March 2020 and the estimated completion date is 20th May 2020
Currently we are working as per the client requirement on day to day bases, code development and build process too are happening day to day basis.
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 08_05_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [10 empty] | Report Date: 8 May, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [9 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 2020-03-04 | 2020-10-04 | 17/04/2020 | 24/04/2020 | 01-05-2020 | 08-05-2020 | 16-05-2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | n | m | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | n | m | A
| m |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; m m: m; A A: A
|  | m |  |  |  | 4 | Test Case Execution | [12 empty] | A | bar: m m
|  | m |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | bar: m m to A A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [12 empty] | A | bar: m m
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | bar: m m to A A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | q | m | A
[5 empty] | m | 9 | Product Delivery | bar: m m to A A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
Any change in the scope will affect the project delivery schedule. | bar: l to n n
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | 08 May'2020 |  | Vivek | Milan
Labels
The project started on 9th March 2020 and the estimated completion date is 20th May 2020
In this week, all the code development activities are completed. All the requested changes in User interface were also completed. Further, testing was not able to start in this week because of non availability of testing resources.
Testing on the project is expected to start from next week.
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 01_05_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [9 empty] | Report Date: 1 May, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [8 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 2020-03-04 | 2020-10-04 | 17/04/2020 | 24/04/2020 | 2020-05-01 | 2020-05-08
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | n | m | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | n | m | A
| m |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  | l: l; m m: m; A A: A
|  | m |  |  |  | 4 | Test Case Execution | [11 empty] | A | bar: m m
|  | m |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | bar: m m to A A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [11 empty] | A | bar: m m
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | bar: m m to A A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | q | m | A
[5 empty] | m | 9 | Product Delivery | bar: m m to A A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
Any change in the scope will affect the project delivery schedule. | bar: l to n n
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 |  | Vivek | Milan
Labels
The project started on 9th March 2020 and the estimated completion date is 20th May 2020
In this week, all the code development activities are completed. All the requested changes in User interface were also completed. Further, testing was not able to start in this week because of non availability of testing resources.
Testing on the project is expected to start from next week.
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 24_04_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [8 empty] | Report Date: 24 April, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [7 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 2020-03-04 | 2020-10-04 | 17/04/2020 | 2020-04-24 | 2020-05-01
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | n | m | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | n | m | A
| m |  |  |  |  | 3 | Build handover session from Dev team to QA team |  | l: l; m: m; A: A
|  | m |  |  |  | 4 | Test Case Execution | [10 empty] | A | bar: m
|  | m |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | bar: m to A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [10 empty] | A | bar: m
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | bar: m to A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | q | m | A
[5 empty] | m | 9 | Product Delivery | bar: m to A
[7 empty] | Risks, Qualitatives, Other Metrics |  | l: Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | The change of priorities may affect the duration of project. | bar: l to n
[6 empty] | 2 | Any change in the scope will affect the project delivery schedule. | bar: l to n
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | 01 May'2020 | Vivek | Milan
Labels
In this week, all the code development activities are completed. All the requested changes in User interface were also completed. Further, testing was not able to start in this week because of non availability of testing resources.
Testing on the project is expected to start from next week.
The project started on 2nd March 2020 and the estimated completion date is 20th May 2020
[11 empty] | m | l | q
[10 empty] | Wingdings | m | l | q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 17_04_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [9 empty] | Report Date: 17 April, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [6 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 2020-03-04 | 2020-10-04 | 17/04/2020 | 24/04/2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | n | m | A | A | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | n | m | A | A | A
| m |  |  |  |  | 3 | Build handover session from Dev team to QA team | [5 empty] | l |  | m | A | A | A
|  | m |  |  |  | 4 | Test Case Execution | [11 empty] | A | bar: m m
|  | m |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | bar: m m to A A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [11 empty] | A | bar: m m
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | bar: m m to A A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | q | m | A | A | A
[5 empty] | m | 9 | Product Delivery | bar: m m to A A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | The change of priorities may affect the duration of project. | bar: l to n n; A A; A A
[6 empty] | 2 | Any change in the scope will affect the project delivery schedule. | bar: l to n n; A A; A A
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | 24 Apr'2020 | Umesh | Vivek | Jay | Milan
Labels
In this week, all the remaining major functionalities are completed. The UI of project is reworked which took 3 additional days.
Testing on the project is expected to start from next week.
The project started on 2nd March 2020 and the estimated completion date is 20th May 2020
[11 empty] | m | l | q
[10 empty] | Wingdings | l: m; l: l; l: q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 10_04_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [9 empty] | Report Date: 10 April, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [5 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 2020-03-04 | 2020-10-04 | 17/4/2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | l | m | A | A | A | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | l | m | A | A | A | A
| l |  |  |  |  | 3 | Build handover session from Dev team to QA team | [5 empty] | l | m | A | A | A
|  | m |  |  |  | 4 | Test Case Execution | [5 empty] | m | m |  |  |  |  | A
|  | l |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | [5 empty] | l | m | A | A | A | A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [6 empty] | m |  |  |  |  | A
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | [6 empty] | m | A | A | A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | m | A | A | A
[5 empty] | m | 9 | Product Delivery | [5 empty] | m | m | A | A | A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | The change of priorities may affect the duration of project. | [7 empty] | A |  | A
[6 empty] | 2 | Any change in the scope will affect the project delivery schedule. | [7 empty] | A |  | A
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | Umesh | Vivek | Jay | Henil | Milan
Labels
In this week, offer integration on data product, Paging, searching and filter on product page, subscription, order detail page, downloading of file management, invoice formatting are comleted in code development. Primary testing on the project has also been started from 8 April.
The next week, all the remaining tasks are expected to finish. Testing, bug fixes will also be started.
[11 empty] | m | l | q
[10 empty] | Wingdings | m | l | q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 03_04_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [12 empty] | Report Date: 03 April, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule | [5 empty] | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 2020-03-04 | 2020-10-04 | 17/4/2020
| l |  |  |  |  | 1 | Code Development |  | l | l | l | l | m | m | A | A | A | A | B | A
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | l | m | m | A | A | A | A |  | A
| m |  |  |  |  | 3 | Build handover session from Dev team to QA team |  | m: m; m: m; A: A; A: A; A: B; A: A | A
|  | m |  |  |  | 4 | Test Case Execution | [13 empty] | A | bar: m to m
|  | m |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | [13 empty] | A | bar: m to A; A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [13 empty] | A | bar: m to m
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | bar: m to A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | m | A | A | B | A
[5 empty] | m | 9 | Product Delivery | bar: m to A
[7 empty] | Risks, Qualitatives, Other Metrics |  | l: Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | The change of priorities may affect the duration of project. | bar: l to l; A; A
[6 empty] | 2 | Any change in the scope will affect the project delivery schedule. | bar: l to l; A; A
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | 17 Apr'2020 | Umesh | Vivek | Prima | Jay | Vikas | Henil | Milan
Labels
The cart management, payment gateway integration and order management is completed for both product. HTML editor for description field is integrated, Content validation for files uploaded is completed, paging and searching in Admin panel is completed. All the email templates has been fixed. Development of some processes took longer than expected. The internal demo with Hiren was also been done, changes has been suggested which would take about a week in code development.
In the major remaining tasks, offer integration on data product, Paging, searching and filter on product page, subscription, order detail page, downloading of file management remains which is expected to be completed in the next week.
[11 empty] | m | l | q
[10 empty] | Wingdings | m | l | q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 27_03_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [10 empty] | Report Date: 27 March, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule |  |  |  |  | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 2020-03-04 | 2020-10-04
| l |  |  |  |  | 1 | Code Development |  | l | l | l | m | m | A | A | A | A | B
| l |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | l | m | m | A | A | A | A
| m |  |  |  |  | 3 | Build handover session from Dev team to QA team | [5 empty] | m | A | A | B | A |  | A
|  | m |  |  |  | 4 | Test Case Execution | [5 empty] | m | [5 empty] | A
|  | m |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | [5 empty] | m | A | A | A | A |  | A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [5 empty] | m | [5 empty] | A
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | [5 empty] | m | A | A | A | A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | A | A | B | A
[5 empty] | m | 9 | Product Delivery | [5 empty] | m | A | A | A | A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | The change of priorities may affect the duration of project. | [6 empty] | A |  |  | A
[6 empty] | 2 | Any change in the scope will affect the project delivery schedule. | [6 empty] | A |  |  | A
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | Umesh | Vivek | Prima | Jay | Vikas | Milan
Labels
In this week, code development for cart management, payment gateway integration and order management has been started which will take about two weeks to complete. At the end of the week, major work on Admin panel has been completed which includes product creation, Offer creation, Category creation and listing of the same.
In the next week, code development for cart management, payment gateway integration and order management is expected to be finished for both products.
[11 empty] | m | l | q
[10 empty] | Wingdings | m | l | q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 20_03_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [10 empty] | Report Date: 20 March, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule |  |  |  |  | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 2020-03-04 | 2020-10-04
| l |  |  |  |  | 1 | Code Development |  | l | l | m | m | m | A | A | A | A | B
| m |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | m | m | m | A | A | A | A
| m |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  |  | m | m | A | A | B | A |  | A
|  | m |  |  |  | 4 | Test Case Execution | [5 empty] | m | [5 empty] | A
|  | m |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | [5 empty] | m | A | A | A | A |  | A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [5 empty] | m | [5 empty] | A
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | [5 empty] | m | A | A | A | A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | A | A | B | A
[5 empty] | m | 9 | Product Delivery | [5 empty] | m | A | A | A | A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | The change of priorities may affect the duration of project. | [6 empty] | A |  |  | A
[6 empty] | 2 | Any change in the scope will affect the project delivery schedule. | [6 empty] | A |  |  | A
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | Umesh | Vivek | Prima | Jay | Vikas | Milan
Labels
In this week, database creation, flow of the processes are decided. Entities and relationship between entities coding has been completed.
In the next week, we will be able to focus on functionality development of the project.
[11 empty] | m | l | q
[10 empty] | Wingdings | m | l | q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics

## 13_03_2020
Copyright OPPM International 2006,2012
[6 empty] | Project Manager: - Pratik Jain |  |  | Project Name: Data-as-a-Service (DaaS) | [10 empty] | Report Date: 13 March, 2020
Project Objective: Development of Data-as-a-Service system where files and APIs can be sold.
`
| Sub-Objectives | [5 empty] | Major Tasks |  | Schedule |  |  |  |  | Owners and Helpers
[9 empty] | 13/03/2020 | 20/03/2020 | 27/03/2020 | 2020-03-04 | 2020-10-04
| l |  |  |  |  | 1 | Code Development |  | l | m | m | m | m | A | A | A | A | B
| m |  |  |  |  | 2 | Code Review and Build deployed on Dev & Test Instances |  |  |  | m | m | m | A | A | A | A
| m |  |  |  |  | 3 | Build handover session from Dev team to QA team |  |  |  |  | m | m | A | A | B | A |  | A
|  | m |  |  |  | 4 | Test Case Execution | [5 empty] | m | [5 empty] | A
|  | m |  |  |  | 5 | Bug Fixes and re-build deployed on both Dev and Test Instances | [5 empty] | m | A | A | A | A |  | A
|  | m |  |  |  | 6 | QA team certifies for internal release of the build | [5 empty] | m | [5 empty] | A
|  |  | m |  |  | 7 | Internal Demo - at the end of Sprint Release | [5 empty] | m | A | A | A | A
|  |  |  | m |  | 8 | Documentation - FRD, Functional Notes, SDD, Test Case Suite, Zoho tasks update |  | m | m | m | m | m | A | A | B | A
[5 empty] | m | 9 | Product Delivery | [5 empty] | m | A | A | A | A
[7 empty] | Risks, Qualitatives, Other Metrics |  |  | Green = Adeque Yellow = Worrisome Red = Dangerous
[6 empty] | 1 | The change of priorities may affect the duration of project. | [6 empty] | A |  |  | A
[6 empty] | 2 | Any change in the scope will affect the project delivery schedule. | [6 empty] | A |  |  | A
# Internal People assigned to the project:
| Code Development & Release | QC & Bug Fixing | Internal Demo | Documentation | Product Delivery |  |  |  | 13 Mar'2020 | 20 Mar'2020 | 27 Mar'2020 | 03 Apr'2020 | 10 Apr'2020 | Umesh | Vivek | Prima | Jay | Vikas | Milan
Labels
The discussion of project started from 09 March,2020. All the requirements are gathered for the project. Initial UI design is decided and work has been started on the same.
Next, we will be working on fixation of UI design and deciding the architecture of project and database creation.
[11 empty] | m | l | q
[10 empty] | Wingdings | m | l | q
Major Tasks
and Risks
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics